SF BAY FIDUCIARY AGENT (FA) REGION

PORT SECURITY GRANT PROGRAM

FY 2009/2010

INVESTMENT JUSTIFICATION REVIEW, APPROVAL AND SUBMISSION SCHEDULE

Feb 12, 2010			FA Files Formal Acceptance for FY 2010 Award w/ FEMA

March 12, 2010	FORMAL FY09/10 IJ’s DUE (electronic filing via grants@sfmx.org)

March 14-16, 2010		Local QA/QC Screening (FA and P/M Team)

March 25-26, 2010		Regional IJ Screening Committee Meets

March 29, 2010		IJ Screening Committee Results Published

March 30-April 11, 2010	Final Package Prep and QA/QC Review

April 12, 2010			Proposed Upload of IJ Projects to FEMA

April 19, 2010			Final FEMA Submittal Date